## Matrix
Team
|  |  | Operations | Stakeholder | Azure DevOps Admin | Team Project Admin | Team Leader/Admin | - Architecture | - Development | - QA | - Implementation | - Security | - Infrastructure
Administration | Organization | Configuration | C |  | A | I | I
|  | Credentials | C |  | R | A | C
|  | Permissions | I |  | R | A | C
|  | PATs (Revoking from other users) | C |  | R | A | C | I | I | I | I | I | I
|  | Integration Features (AAD, ER, OAuth) | C | bar: R R
Standard's Governance | bar: R R to A A
Team Projects | bar: R R to A A
|  | Extensions | C |  | R | A | I | I | I | I | I | I | I
|  | Access and Connectivity | C |  | A | C | I | I | I | I | I | I | I
|  | Licensing |  |  | A | C | C | I | I | I | I | I | I
Billing | bar: R R
Auditing | bar: R R
|  | Shared Components | C |  | R R: R; A A: A; C C: C
Custom Process Templates | bar: R R to A A
Service Healths | bar: R R

## Description
Suggested Roles | Operations | Different IT teams supporting daily tasks at the company, this normally includes Security, Communications, DBAs, Server Administration, User Management, etc.
| Stakeholder | Business Users, product owners.
| Azure DevOps Admin | Person or team in charge of managing features and global options for the Azure DevOps organization.
| Team Project Admin | Person or team in charge of a Team Project, managing several software solutions, users, etc.
| Team Leader/Admin | Person or team in charge of managing tasks and people working on a specific software solution.
| Team | Different people directly involved on a project, capable of transforming requirements on business value in an autonomous way.
| - Architecture | People providing guidelines and helping solve problems. Normally individuals from Architecture division are assigned a weekly amount of hours to work on teams.
| - Development | People in charge of actual coding.
| - QA | People in charge of testing and validating functionality of software solution.
| - Implementation | People dedicated to automate the deployment of software on different environments. Normally with a counterpart in Operations for solutions not under DevOps.
| - Security | People providing guidelines, helping and reviewing how security is proactively applied. Normally individuals from Security division are assigned a weekly amount of hours to work on teams.
| - Infrastructure | People helping to define infrastructure components according to company standards. Normally individuals from Infrastructure division are assigned a weekly amount of hours to work on teams.
Activities
Organization Administration | Configuration | Basic configuration tasks including organization name, URL management, time zone (important for task's synchronization), region (where data reside) and organization owner. | Link
| Credentials | User management, defining access levels. | Link
| Permissions | Managing membership for collection level security group | Link
| PATs (Revoking from other users) | Revoking PATs from other users whether because they are no longer needed or they have become compromised. | Link
| Integration Features (AAD, ER, OAuth) | Manage or coordinate integration futures primarily Azure Active Directory, but also including the use of ExpressRoute and Oauth (Currently only against Github Enterprise Server) | Link
| Standard's Governance | Manage and organize company wide standards, baselines to measure maturity level, documentation and processes created to implement a DevOps strategy. | Link
| Team Projects | Creation and management of Team Projects | Link
| Extensions | Discover, manage, install and evaluate required extensions. | Link
| Access and Connectivity | Manage policies to access resources on the organization. | Link
| Licensing | Manage the purchase of components within Azure DevOps (Users, Test plans, Parallel jobs, Hosted agents, Artifacts, Extensions, etc.) | Link
| Billing | Accountability and reporting of the purchases for Azure DevOps in a given subscription | Link
| Auditing | Proactively review audit logs. | Link
| Shared Components | Manage (install, configure and maintain) Agent/Deployment Pools and Global Notifications available organization wide. | Link
| Custom Process Templates | Define, extend and maintain process template that require customization to adhere to specific requirements. Manage Team Projects using this custom templates. | Link
| Service Healths | Proactively review usage logs to try to anticipate throttle conditions. | Link